## Scope & Scenario
# | Scope | # | Scenario | # | Scenario sub | # | Scenario sub 2
1 | Credit Card Fulfillment | a | Normal Process
|  | b | Card Deposit Sequence | i | Normal card sequence
|  |  |  | ii | With Invalid Card
|  | c | Block code | i | No Block Code
|  |  |  | ii | Block T
|  |  |  | iii | Block M
|  |  |  | iv | Block P
|  |  |  | v | Block E
|  | d | BO checking - Fulfillment Record
|  | e | Cardlink
|  | f | Reports | i | GL report
|  |  |  | ii | Cardlink Recon Report
2 | Saving Account Fulfillment | a | Normal Process
|  | b | Deposit Sequence | i | Normal Saving Accounts sequence
|  |  |  | ii | With Invalid Saving Accounts
|  | c | BO checking - Fulfillment Record
|  | d | Host
|  | e | Reports | i | GL report
|  |  |  | ii | Cardlink Recon Report
3 | Current Account Fulfillment | a | Normal Process
|  | b | Deposit Sequence | i | Normal Current Accounts sequence
|  |  |  | ii | With Invalid Current Accounts
|  | c | BO checking - Fulfillment Record
|  | d | Host
|  | e | Reports | i | GL report
|  |  |  | ii | Host Recon Report
4 | Product Sequence | a | Result to Saving (Saving + Current + Cr Card)
|  | b | Result to Current (Invalid Saving + Current + Cr Card)
|  | c | Result to Credit Card (Invalid Saving & Current + Cr Card)
5 | Product Types testing | a | Credit Cards | i | Master Card
|  |  |  | ii | Visa Card
|  |  |  | iii | DCC Card
|  | b | Saving Accounts | i | Normal Saving
|  |  |  | ii | MCSSA
|  | c | Current Accounts | i | Normal Current Accounts
|  |  |  | ii | Now Account
|  | d | Other Accounts | i | More money
|  |  |  | ii | Loans
|  |  |  | iii | One Account
|  | e | Currency testing | i | HKD
|  |  |  | ii | Non HKD
6 | Notifications | a | MGM Promotion message to 3in1 NTB | i | Contents | A | SMS
[6 empty] | B | Email
|  |  |  | ii | SMS
|  |  |  | iii | Email
|  |  |  | iv | Opt Out
|  | b | MGM registration message | i | Contents | A | SMS
[6 empty] | B | Email
|  |  |  | ii | SMS
|  |  |  | iii | Email
|  |  |  | iv | Opt Out
|  |  |  | v | Staff
|  | c | Reward earned | i | Contents | A | SMS
[6 empty] | B | Push Notification
|  |  |  | ii | SMS
|  |  |  | iii | Push Notification | A | Pre-login
[6 empty] | B | Post-login
|  |  |  | iv | Opt Out
|  |  |  | v | Mission Completed
|  |  |  | vi | Staff
|  |  |  | vii | Rejoiner
|  |  |  | viii | Rejoiner (PC)
|  |  |  | ix | BOM check list
|  | d | Expiring mission reminder | i | Contents | A | SMS
[6 empty] | B | Email
[6 empty] | C | Variables changed
|  |  |  | ii | SMS
|  |  |  | iii | Email
|  |  |  | iv | Opt Out
|  |  |  | v | Mission Completed
|  |  |  | vi | Staff
|  |  |  | vii | BOM check list
7 | Entry Point | a | Pre-login | i | Reward Go' button
|  |  |  | ii | 'Reward Station' banner
|  |  |  | iii | Side bar | A | Invite Your Friend
[6 empty] | B | Reward & History
[6 empty] | C | Rewards Notification
|  | b | Post login | i | Reward Go' button
|  |  |  | ii | 'Reward Station' banner
|  |  |  | iii | Reward Go' complete mission bar
|  |  |  | iv | Side bar | A | Invite Your Friend
[6 empty] | B | Reward & History
[6 empty] | C | Rewards Notification
|  | c | First time login MGM | i | Welcome message
|  | d | Additional
|  | e | Mission expired
|  | f | Page movement
8 | Statements | a | Saving account statement
|  | b | Current account statement
|  | c | Credit card statement
|  | d | Consolidation statement
9 | Referee | a | 3 in 1 referral code testing | i | Mobile input screen | A | Valid referral code
[6 empty] | B | Invalid referral code
[6 empty] | C | Blank
|  |  |  | ii | Confirmation screen | A | Valid referral code
[6 empty] | B | Invalid referral code
[6 empty] | C | Blank
|  | b | ETB InMotion registration
|  | c | Referee as a rejoiner
10 | BO | a | Gamification Management | i | Screen design
|  |  |  | ii | Mission Management | A | View Mission
[6 empty] | B | View Level
[6 empty] | C | Download Ineligible Fulfillment CSV
[6 empty] | D | First time activation
[6 empty] | E | De-activation
|  | b | Gamification Activities Log | i | Gamification Enquiry | A | Screen Layout
[6 empty] | B | Result verification
|  |  |  | ii | Gamification Report - Mission Report | A | Screen Layout
[6 empty] | B | Result verification
|  |  |  | iii | Gamification Report - Fulfillment Report | A | Screen Layout
[6 empty] | B | Result verification
[6 empty] | C | Download CSV
|  | c | Relationship linkage
|  | d | Account Opening EAO Application Inquiry | i | Bundle EAO - Search result summary
|  |  |  | ii | Bundle EAO - Individual bundled record
|  |  |  | iii | Bundle EAO - Individual EAO record
|  |  |  | iv | Bundle EAO - Individual VCC record
11 | Referer | a | Mission Screen | i | Screen Layout
|  |  |  | ii | Mission list - Money earned
|  |  |  | iii | Mission list - Single/Multiple Mission
|  |  |  | iv | Mission list - Individual Mission | A | Mission name & info
[6 empty] | B | Mission complete count
[6 empty] | C | Time count
|  | b | Mission Details | i | MGM registration & TnC
|  |  |  | ii | Mission Info
|  |  |  | iii | Mission complete status
|  |  |  | iv | Time counter
|  |  |  | v | Referral code
|  |  |  | vi | Referral count
|  |  |  | vii | Rebate count
|  |  |  | viii | TnC & Remarks
|  |  |  | ix | Refer button
|  |  |  | x | Expired Mission
|  | c | Reward History | i | Without reward history
|  |  |  | ii | With reward history | A | Sorting
[6 empty] | B | Information
|  | d | Reward Notification | i | Without reward record
|  |  |  | ii | With reward record | A | Sorting
[6 empty] | B | Information
12 | Reports | a | Host recon report | i | Daily Recon Report
|  |  |  | ii | Monthly Recon Report
|  | b | Cardlink recon report | i | Daily Recon Report
|  |  |  | ii | Monthly Recon Report
|  | c | InMotion recon report | i | Daily Recon Report
|  |  |  | ii | Monthly Recon Report
|  | d | GL report | i | Host GL report
|  |  |  | ii | Cardlink GL report
|  | e | Fulfillment Alert Report
|  | f | MGM Auditor Report
|  | g | MGM NTB Report
|  | h | MGM Referee Report
|  | i | Referral Code Activator Report
13 | Data Retention | a | 180 days records | i | Reward History
|  |  |  | ii | Reward Notification
|  | b | 1 year records | i | Mission management
|  |  |  | ii | Gamification Activities Log - Gamification Enquiry
|  |  |  | iii | Gamification Activities Log - Gamification Report - Mission Report
|  |  |  | iv | Gamification Activities Log - Gamification Report - Fulfillment Report
14 | Others | a | CMS switching | i | CMS switching
|  |  |  | ii | Mission 1 stage
|  |  |  | iii | No mission stage
|  |  |  | iv | Mission 2 stage
|  | b | Staff as referrer | i | Employee referrer
|  |  |  | ii | Director referrer
|  |  |  | iii | Officer referrer
|  | c | Manual suspense list
|  | d | VCC submission
|  | e | BO edit log
|  | f | CMS
|  | g | Push Notification
|  | h | Screen Verification
|  | i | LG mobile
Estimation
7 profiles required for testing (Profile A, B, C, D, E, F & G)
Profile A - NTB, language in Eng, able to receive all 4 types of msg
Profile B - NTB, language in TC, able to receive all 4 types of msg
Profile C - NTB, language in SC, able to receive all 4 types of msg
Profile D - NTB, any language, Opt Out all notifications
Profile E - Mission Completed
Profile F - Staff
Profile G - RMID listed in BOM check list

## UAT Status
Progress Status as of 2-2-2021
Project Name | Start Date | End Date | Total Testing Date | Testing Date | Total Case number | Total Executed cases | Run Rate | Execution Rate | Pass Rate (Pass/Executed) | Pending Rate (Pending/Executed) | Fail Rate (Fail/Executed)
InMotion MGM MVP1 | 2020-09-21 | 2020-11-11 | 35 | 96 | 0 | 0 | 274.3% |  | 0% | 0% | 0% | 2020-10-01
2020-10-02
2020-10-26
Daily Status
Executed Case | Passed Case | Pending Case | Failed Case
0 | 0 | 0 | 0
Project Status
Test Application | Planned Case number | Total Executed | Cancelled | Passed Case | Pending Case | Failed Case | Not Executed | Pass Rate (Pass/Executed) | Pending Rate (Pending/Executed) | Fail Rate (Fail/Executed)
Fulfillment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Notifications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Entry Point | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Statements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Referee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
BO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Referrer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Reports | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Data Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Formulas:
Total Testing Date = NETWORKDAYS([Start Date],[End Date],W1:W24)
Testing Date = [Total Testing Date]-NETWORKDAYS(TODAY(),[End Date],W1:W24)+1

## Test Cases
# | Scope | Ref.# | Testing Focus | Lang. | OS | Scenario | Conditions | Conditions 2 | Test Steps | Expected Result | Test Date | Result | Remarks
001 | Company Information Section upto field number 16 - Appointment Form | 1 | To verify the field labels and validation for company information section upto field number 16. | Any | Any | Field and Functional validation |  |  | 1. Open the online appointment form page 2. Verify that the title of first section of the appointment form is “Company Information”. 3. Verify that the input field with label “Company Name in English” is displayed. 4. Verify that company name in English field is mandatory and accepts 100 alphanumeric characters. 5. Verify that if the English Company Name is invalid then the error message “Please input your English company name” will be displayed to the user. 6. Verify that the input field with label “Company Name in Chinese” is displayed. 7. Verify that Company name in Chinese field is optional field and accepts 100 alphanumeric characters. 8. Verify that a drop down field with the label “Type of Entity” is displayed to the user. 9. Verify that the drop down values are : Limited Company Partnership Sole proprietorship Society / Club / Association Others 10. Verify that the Type of Entity field is a mandatory field and if you do not select any valid value then the error message “Please select your company's constitution” is displayed. 11. Verify that a new input field is displayed to the user if the user select “Others” in the Type of Entity field. 12. Verify that the new field is mandatory and Error message “Please specify your company's constitution” is displayed to the user when the user does not enter anything in the newly displayed field. 13. Verify that two fields are displayed for contact number with label “Office Telephone number”. One is the drop down for the country code and the other is for the number. 14. Verify that the country code drop down field contains : +852, +853 , +86 and Others as values 15. Verify the Contact number field accepts 8 digit number if the area code is +852 or +853 and accepts 11 digit number if the area code is +86 and 20 digits for Others 16. Verify that the area code and number both are mandatory fields. If number field is filled with invalid value then the error message “Please input a valid phone number” is displayed to the user. 17. Verify that the calendar field is displayed with label “Date of Incorporation”. 18. Verify that the date field is mandatory and if not filled then the error message “Please select date of incorporation” is displayed to the user. 19. Verify that an input field is displayed with label “Place of Incorporation”. 20. Verify that the place of incorporation field is mandatory and if not filled then the error message “Please select country of incorporation” is displayed to the user. 21. Verify that an input field is displayed with label “Office Address”. 22. Verify that the office address field is mandatory and if not filled then the error message “Please input registered address” is displayed to the user. 23. Verify that an input field is displayed with label “Place of Business / Industry”. 24. Verify that an input field is displayed with label “Nature of Business/Industries”. 25. Verify that Nature of Business/Industries field is mandatory and if not filled then the error message “Please select the nature of Business/Industries” is displayed to the user. 26. Verify that an input field is displayed with label “Nature of Products/Services offered”. 27. Verify that Nature of Products/Services offered field is mandatory and if not filled then the error message “Please input the nature of Products/Services offered” is displayed to the user. 28. Verify that an input field is displayed with label “Annual Sales Turnover (HKD)”. 29. Verify that input field for turnover is mandatory and if not filled then the error message “Please input the Annual Sales Turnover (HKD)” is displayed to the user. 30. Verify that an input field is displayed with label “Annual Net Profit (HKD)”. 31. Verify that input field for annual profit is mandatory and if not filled then the error message “Please input the Annual Net Profit (HKD)” is displayed to the user. 32. Verify that a drop down field with the label “Purpose of Account opening” is displayed to the user. 33. Verify that the drop down values are : Savings Investment Business Operation Loan Payment Payroll Payment Settlement Others 34. Verify that the field Purpose of Account Opening is a mandatory field and if you do not select any valid value, then the error message “Please select the Purpose of Account opening” is displayed. 35. Verify that if the user selects “Others” in the Purpose of Account Opening field then a new input field is displayed to the user for entering the response. 36. Verify that if the user does not enter anything in the Others input field then the error message “Please specify the purpose of account opening.” 37. Verify that the input field with label “Name of Company Secretary” is displayed. 38. Verify that field Name of Company Secretary is optional field and accepts 100 alphanumeric characters. | 1. The new online appointment form page should be opened. 2. Title of the first section of the form is verified. 3. Field does display with correct label. 4. Verified 5. Error message verified. 6. Field does display with correct label. 7. Verified 8. Drop down field does display. 9. Drop down values have been verified succesfully 10. Message is verified successfully for Type of Entity field. 11. New field does display when the user select Others in the Type of Entity. 12. Error message verified. 13. Two fields does display for telephone number. 14. Drop down values verified 15. Verified the number limit based on area code 16. Error message verified. 17. Date fields does display and label is verified. 18. Error message is verified successfully. 19. Input fields does display and label is verified. 20. Error message is verified successfully. 21. Input fields does display and label is verified. 22. Error message is verified successfully. 23. Input fields does display and label is verified. 24. Input fields does display and label is verified. 25. Error message is verified successfully. 26. Input fields does display and label is verified. 27. Error message is verified successfully. 28. Input fields does display and label is verified. 29. Error message is verified successfully. 30. Input fields does display and label is verified. 31. Error message is verified successfully. 32. Drop down field does display. 33. Drop down values have been verified succesfully 34. Message is verified successfully for Type of Entity field. 35. The filed does display to the user 36. Error message is verified successfully. 37. Field does display with correct label. 38. Verified |  | pass
002 | UI verification of the Appointment Form | 2 | To verify that the UI of the appointment form is aligned with the design. | Any | Any | UI verification |  |  | 1. Open the online appointment form page 2. Verify that the top right corner of the page has the link for 3 languages i.e. English, Traditional Chinese and Simplified Chinese. 3. Click on any of the available Links and verify that the language of the page has been changed successfully. 4. Now enter the data in the first section of the form and complete it. 5. Verify that the tick mark is displayed on the left side of the page when a section of the form is completed. | 1. Form page is opened 2. Links for changing the language does display. 3. Language changed. 4. A section of the form is completed. 5. Tick mark is displayed. |  | pass
003 | Company Information Section remaining fields - Appointment Form | 3 | To verify the field labels and validation for the remaining fields of company information section | Any | Any | Field and Functional validation |  |  | 1. Open the online appointment form page 2. Fill in the fields till number 17 and verify that the user us able to see the field number 18 with the label “Does your company engage in money / currency exchange, money transfer or remittance agent services?” 3. Verify that this field has 2 radio buttons with values Yes and No. 4. Verify that the filed is mandatory and her gets the error message “Please indicate your business.” If no option are selected. 5. Verify that the user us able to see the field number 19 with the label “Is your company with 5 or more layers in its ownership / controlling structures?” 6. Verify that this field has 2 radio buttons with values Yes and No. 7. Verify that the filed is mandatory and her gets the error message “Please indicate your company structure.” If no option are selected. 8. Verify that the user us able to see the field number 20 with the label “Is your company directly or indirectly owned by trust or foundation arrangement?” 9. Verify that this field has 2 radio buttons with values Yes and No. 10. Verify that the filed is mandatory and her gets the error message “Please indicate your company structure.” If no option are selected. 11. Verify that the user us able to see the field number 21 with the label “Does your company have any nominee shareholders in the ownership structure?” 12. Verify that this field has 2 radio buttons with values Yes and No. 13. Verify that the filed is mandatory and her gets the error message “Please indicate your company structure.” If no option are selected. 14. Verify that the user us able to see the field number 22 with the label “Has your company issued Bearer shares?” 15. Verify that this field has 2 radio buttons with values Yes and No. 16. Verify that the filed is mandatory and her gets the error message “Please indicate your company structure.” If no option are selected. 17. Verify that the user us able to see the field number 22 with the label “Please select you interested banking services (multiple options are allowed)” 18. Verify that this field has multiple checkboxes and user can select more than one checkbox. 19”. Verify that the options for this field are : General Banking Services: Deposit Products Foreign Currency Exchange Payroll Financing Services: Loan Services Trade Finance Insurance Services: Life Insurance General Insurance Investment Services: Securities Funds Structured Products Others:" 20. Verify that this will be an optional field. 21. Verify that if the user select “Others” option in the above field then an additional input field is displayed to the user. 22. Verify that this additional field is optional and can accept 100 character of type String. | 1. The new online appointment form page should be opened. 2. Field is displayed to the user. 3. Radio buttons verified with Yes and No options 4.Error message verified. 5. Field is displayed to the user. 6. Radio buttons verified with Yes and No options 7. Error message verified. 8. Field is displayed to the user. 9. Radio buttons verified with Yes and No options 10. Error message verified. 11. Field is displayed to the user. 12. Radio buttons verified with Yes and No options 13. Error message verified. 14. Field is displayed to the user. 15. Radio buttons verified with Yes and No options 16. Error message verified. 17. Field is displayed to the user. 18. Radio buttons verified with Yes and No options 19. Options verified 20.Verified. 21. Input field does display. 22. Verified. |  | pass
004 | Relevant Individual Section | 4 | To verify the field labels and validation for the Relevant Individual Section. | Any | Any | Field and Functional validation |  |  | 1. Open the online appointment form page 2. Fill in the company information and navigate to the relevant individual section. 3. Verify that the field label “Position” is displayed under the relevant individual section 4. “Verify that the below checkboxes are displayed for the position field: Contact Person Director Shareholder Sole Proprietor Partner" 5. Verify that user can check multiple checkboxes and minimum 1 is required. If the user does not select any checkbox then error message “Please indicate your position.” will be displayed. 6. Verify that the label Name is displayed in the relevant individual section and it accepts 100 character of type String. 7. Verify that name field is mandatory and gives the error message “Please input your name.” If user doesn’t enter Name. 8. Verify that the field "Office Telephone number” and “Mobile Number” are displayed to the user. 9. “Verify that both these fields have drop down with values : +852 +853 +86 Others" 10. Verify that the input field for the number accepts 8 digit for +852 and +853 code and 11 digit for +86 code. And if user select others then the input field accepts 20 digit starting with + sign. 11. Verify that the mobile number and office number fields are mandatory and if the user does not enter nay value then the error message “Please input a valid phone number.” Is displayed. 12. Verify that the Email address field is displayed under the relevant individual section. 13. Verify that the email field is mandatory and accepts 100 characters of type String. If the email address is not entered or invalid the error message “Please input a valid email.” Is displayed. 14. Verify that the Job title field is displayed to the user. Also check that its mandatory and accepts 100 character of type String. 15. Verify that if Job Title field is empty then error message “Please input your job title.” Is displayed to the user. 16. Verify that upto 5 Relevant Individual information can be added. | 1. Appointment form opened. 2. User moved to relevant individual section 3. Field does display 4. Checkboxes are verified. 5. Error message verified. 6. Name field is displayed 7. Error message verified. 8. Fields does display 9. Drop down values verified. 10. Verified 11. Error message verified. 12. Email field is displayed. 13. Error message verified. 14. Job title field is displayed and accepts 100 string characters 15. Error message verified. 16. Verified |  | pass
005 | Acknowledgment Page | 5.a | Verify that the user is able to see the acknowledgement page after submitting the appointment form. | Any | Any | Functional Verification |  |  | 1. Open the online appointment form page. 2. Enter the company information and relevant individual and make sure there is no error. 3. Enter the captcha and submit the form. 4. Verify the design and layout of the acknowledgement page. 5. Verify that there is an unique ID displayed on the acknowledgement page. | 1. The new online appointment form page should be opened. 2. Details filled successfully. 3. User should be navigated to the Acknowledgement page. 4. Look and feel of the page should match with the expected design. 5. Unique ID does display. |  | pass
006 | Acknowledgment Page | 5.b | To verify that the language of the acknowledgement page depends on the language we had selected on the appointment form. | Any | Any | Functional Verification |  |  | 1. Open the online appointment form page. 2. Select any language on the appointment form. 3. Enter the company information and relevant individual and make sure there is no error. 4. Enter the captcha and submit the form. 5. Verify that the language of the acknowledgement page is similar to that of the appointment page. | 1. The new online appointment form page should be opened. 2. Language of the appointment form changed. 3. Details filled successfully. 4. User should be navigated to the Acknowledgement page. 5. The language is similar to appointment form page. |  | pass
007 | Acknowledgment Email | 6.a | Verify that the email is sent to user after the successful application of the appointment form. | Any | Any | Functional Verification |  |  | 1. Open the online appointment form page. 2. Enter the company information and relevant individual and make sure there is no error. 3. Enter the captcha and submit the form. 4. Verify that there is an unique ID displayed on the acknowledgement page. 5. Now verify that the email is sent to the email address provided in the relevant individual section. 6. Verify that the Unique ID in the email and Unique ID on the acknowledgement page are same. | 1. The new online appointment form page should be opened. 2. Details filled successfully. 3. User should be navigated to the Acknowledgement page. 4. Unique is displayed. Note down the unique ID 5. User received the email. 6. Unique IDs match. |  | pass
008 | Acknowledgment Email | 6.b | Verify that the email is not sent to the user if the form is not submitted or there is some validation error. | Any | Any | Functional Verification |  |  | 1. Open the online appointment form page. 2. Enter the company information and relevant individual and leave a mandatory field blank or enter invalid value in one of the fields. 3. Enter the captcha and submit the form. 4. Verify that the acknowledgment email is not sent to the user. | 1. The new online appointment form page should be opened. 2. Form is filled with one invalid value or blank value. 3. User should get an error message. 4. User does not receive any email in case there is any error. |  | pass
009 | File Upload | 7.a | Verify that the user is getting option to upload the files in the appointment form and is able to upload a file successfully. | Any | Any | Functional Verification |  |  | 1. Open the online appointment form page. 2. Enter the company information and relevant individual and make sure there is no error. 3. Verify that just below the relevant individual section, there is an option to upload the files. 4. Verify that file upload is not mandatory. 5. Now upload a sample file and submit the form. | 1. The new online appointment form page should be opened. 2. Details filled successfully. 3. File upload option is displayed. 4. User should be able to submit the form without file upload. 5. Form is submitted successfully and user receives an acknowledgement email. |  | pass
010 | File Upload | 7.b | Verify the validations for file upload | Any | Any | Field validation |  |  | 1. Open the online appointment form page. 2. Fill in all the details and navigate to the file upload section 3. Verify that the user can upload upto 5 files with max 10 mb for all the files. 4. Verify that is the user is uploading a single file then the file can be max of 10 mb. 5. Verify that the File Name can only contain English, numeric characters, space or specific symbols including !@#$%^&()_+=-[]{};',. 6. Verify that the supported format of files are pdf; bmp; jpg; jpeg; png; tif; tiff 7. Verify that if any of the validation is not matched then the user gets error messages from below : “Incorrect file name.” , “Incorrect file format.” , “File size exceeds 10MB.” and “The uploaded file does not match the requirements (Total size > 10MB). Please retry.” 8.Verify that if the file name is too long then the UI should not be disturbed while uploading it. 9. Verify that while deleting the file user gets a pop up with the message “Are you sure you want to remove this file?”. 10. Verify that there are 2 buttons on the pop up, Yes and No. If user selects Yes then the file is deleted and if No then file is not removed. | 1. The new online appointment form page should be opened. 2. User navigated to file upload section after filling all other details correctly. 3. Verified. 4. Verified 5. Verified 6. Verified. 7. Verified. 8. Verified 9. Verified. 10. Verified. |  | pass
011 | Submit and Reset Buttons | 8 | Verify the Submit and Reset button and their functionality | Any | Any | Functional Verification |  |  | 1. Open the online appointment form page. 2. Fill in all the details and navigate to the bottom of the page. 3. Verify that there are 2 buttons “Reset” and “Submit” available at the bottom. 4. Verify that if the user click reset button, a pop up is displayed to the user with Yes and No option and the message “Are you sure you want to reset the form?” 5. Select Yes on the pop up and verify that the form is reset to blank. | 1. The new online appointment form page should be opened. 2. User reached the bottom of the page. 3. Buttons are present 4. Pop up and the messages are verified. 5. Form is reset and all fields are blank. |  | pass
012 | Left Side Progress Menu | 9.a | Verify that the progress menu and the text on the left side is displayed even after scrolling down. | Any | Any | Functional Verification |  |  | 1. Open the online appointment form page. 2. Fill in the form with company information and relevant individual information and scroll down. 3. Verify that when the user scroll down on the page, the left side menu and the text is not scrolled up and is visible to the user. | 1. The new online appointment form page should be opened. 2. User scrolled down on the appointment form 3. Left side menu and the text is visible to the user. |  | pass
013 | Left Side Progress Menu | 9.b | Verify that the left side menu will not be visible if the screen is small. | Any | Any | Functional Verification |  |  | 1. Open the online appointment form page in a small screen such as mobile. 2. Change the language to English. 3. Scroll down on the application page. 4. Verify that the left side progress menu is not displayed to the user. | 1. The new online appointment form page should be opened. 2. Language changed 3. Application page scrolled down. 4. The progress menu is not displayed. |  | pass
014 | Jump to Error | 10 | Verify that the user is jumped to the section where the error is occurred. | Any | Any | Functional Verification |  |  | 1. Open the online appointment form page. 2. Fill the form and leave one of the mandatory field blank in the company information section. 3. Check the TnC checkbox and click the submit button 4. Now fill the blank field of company information section and leave one mandatory field blank in the Relevant individual section. 5. Now submit the form and verify that the user is scrolled up to the field where error has occurred. | 1. The new online appointment form page should be opened. 2. Form is filled completely. 3. Error is occurred and the form is scrolled to the field where the error has occurred. 4. Field is left blank in the relevant individual section 5. User scrolled up to the field with error, under the Relevant individual section. |  | pass
015 | Monthly Statistic report | 11 | Verify the monthly statistic report | Any | Any | Functional Verification |  |  | 1. Connect to UAT database. 2. Run the following queries on the database: select * from TBL_SYS_PROPS where PROPERTY_KEY = 'ONLAPPT.MONTHLY_USAGE'; select * from TBL_SYS_PROPS where PROPERTY_KEY = 'ONLAPPT.MONTHLY_USAGE_RECIPIENTS'; 3. Verify that the number of records in the monthly report received via email is matching with the number of record in the database. 4. Submit a form and then repeat the steps above o see that the number of records are matching. | 1. Connected to database successfully 2. Queries executed successfully 3. Number of data is matching. 4. Verified. |  | pass

## System Incident Log
System Down Time
System healthy rate 81.67 %
Day | Date | Incident Time | Impacted (Hrs) | Issue | Impacted Area | Root Cause
1 | 2020-09-21 | 0900-1800 | 8 | Unable to login testing profiles | All UAT blocked | Bug in acctBalanceSumm API.
2 | 2020-09-22 | 0900-1800 | 8 | Unable to login testing profiles | All UAT blocked | Bug in acctBalanceSumm API.
3 | 2020-09-23 | 0900-1130 | 2.5 | Unable to open InMotion | All UAT blocked | SZ electricity shutdown last night, server is rebooting
4 | 2020-09-24 | 1400-1545 | 1.75 | Unable to load InMotion pre-login | All UAT blocked | New InMotion ver2.0.3 is updated
5 | 2020-09-25 | 1400-1800 | 5 | Unable to load InMotion pre-login | All UAT blocked | FIRCO timeout
6 | 2020-09-28 | 0900-1200 1200-1800 | 8 | Unable to load InMotion 3 in 1 process blocked (SYS100) | All UAT blocked Fulfillment cases blocked | FIRCO timeout
7 | 2020-09-29 | 0900-1200 1600-1800 | 5 | 3 in 1 process blocked (SYS100) AUTH999 | Fulfillment cases blocked | SZDC deployment
8 | 2020-09-30 | 1100-1400 1530-1800 | 4.5 | InMotion Login failed System Maintenance | All UAT blocked All UAT blocked | SZDC deployment
9 | 2020-10-05 | 0900-1800 | 8 | System Maintenance - Unable to open InMotion | All UAT blocked | SZDC relocation of data center is not fully completed
10 | 2020-10-06 | 0900-1700 | 7 | System Maintenance - Unable to open InMotion | All UAT blocked | SZDC IP connection issue
11 | 2020-10-07 | 0900-1700 | 7 | 3 in 1 process blocked (SYS999) | Fulfillment cases blocked | MQ issue
12 | 2020-10-08 | 0900-1400 1400-1430 1530-1700 | 6 | Unable to complete 3 in 1 account opening Unable to proceed UAT Unable to place 3 in 1 account opening & BO | Fulfillment cases blocked All UAT blocked Fulfillment cases blocked | Environment changed to AVQFMG for squad 5 UAT SZDC deployment System B/E deployment
13 | 2020-10-09 | 0900-1130 | 2.5 | Unable to login InMotion | All UAT blocked | CA server issue
14 | 2020-10-12
15 | 2020-10-13 | 1000-1500 | 5 | Unable to login inMotion (SSO500) | All UAT blocked | PIB is down
16 | 2020-10-14
17 | 2020-10-15 | 1400-1630 | 2.5 | Unable to login inMotion (AUTH999) | All UAT blocked | UAT deployment
18 | 2020-10-16 | 1000-1100 1130-1500 | 4.5 | Unable to land to Reward Go! (SYS106) Environment incorrect switch to UAT3 | Fulfillment cases All UAT blocked | Session token issue UAT deployment
19 | 2020-10-19 | 1530-1700 | 1.5 | Unable to login inMotion (SSO500) | All UAT blocked | PIB is down
20 | 2020-10-20
21 | 2020-10-21 | 0900-1030 1430-1600 | 3 | Unable to login InMotion Unable to land to Reward Go! | All UAT blocked All UAT blocked | Issue caused by 20oct release Network connection issue
22 | 2020-10-22
23 | 2020-10-23 | 0900-1530 1530-1800 | 8 | InMotion response slow / Unable to login InMotion under AOS response slow | All UAT blocked UAT related to AOS | Oct prod release - resource prioritize to SZDC Network issue
24 | 2020-10-27
25 | 2020-10-28
26 | 2020-10-29 | 1400-1500 | 1 | Unable to login InMotion | All UAT blocked | SZDC deployment
27 | 2020-10-30 | 0900-1100 | 2 | Unable to login InMotion | All UAT blocked | Host dark time
28 | 2020-11-02 | 0900-1530 1400-1800 | 8 | Skip function removed from 3in1 application Unable to perform 3in1 EAO | Referral action blocked EAO blocked | Issue on version control Avaloq unable to create account
29 | 2020-11-03 | 0900-1800 | 8 | Unable to perform 3in1 EAO | EAO blocked | Avaloq unable to create account
30 | 2020-11-04 | 0900-1600 1400-1800 | 8 | Unable to perform 3in1 EAO 3in1 application with referral code no captured | EAO blocked All UAT blocked | Avaloq unable to create account Code release for Nov version removed MGM coding
31 | 2020-11-05 | 0900-1400 1700-1730 | 4.5 | 3in1 application with referral code no captured InMotion slow response unable to login | All UAT blocked All UAT blocked | Code release for Nov version removed MGM coding Connection issue
32 | 2020-11-06 | 1030-1800 | 6.5 | Unable to login InMotion | All UAT blocked | Connection issue
33 | 2020-11-09
34 | 2020-11-10 | 1200-1500 | 5 | Unable to login InMotion | All UAT blocked | SZDC deployment
35 | 2020-11-11
|  | Total lost | 140.75 | Hours | out of 768 hours
* Counting based on 8 working hours per day (1300-1400 lunch hour)